## Bug Reports
🐛 OpenCart Demo – Bug Report Tracker
Site: https://demo.opencart.com/ ¦ Version: OpenCart 4.x ¦ Generated: 2026-05-08
Bug ID | Title | Module | Severity | Priority | Status | Environment | Steps to Reproduce | Expected Result | Actual Result | Related TC | Reported By | Date Reported | GitHub Issue / Ref | Notes / Fix Hint
BUG-001 | Mini-cart does not update after Add to Cart | Shopping Cart | Critical | P1 | Open | Chrome latest / Safari / Android & iOS | 1. Open demo.opencart.com 2. Click 'Add to Cart' on any featured product on Home page 3. Observe header cart icon and mini-cart dropdown | Cart icon count increments to 1. Mini-cart shows the added product. | Success notification appears BUT mini-cart remains empty (0 items). Cart icon does not update. Bug confirmed on both desktop and mobile. | TC-SC-001 / TC-HP-011 | QA Team | 2026-05-08 | GH #11418 / Forum OC4 | AJAX response likely not refreshing cart widget. Check cart.js update callback.
BUG-002 | Search returns SQL SQLSTATE[HY093] server error | Search | Critical | P1 | Open | All browsers – demo.opencart.com | 1. Type any keyword in the search box (e.g. 'laptop') 2. Click the Search button | Search results page displays matching products. | Server throws Exception: SQLSTATE[HY093] – 'number of bound variables does not match number of tokens'. Raw SQL error exposed to the user. | TC-SN-001 | QA Team | 2026-05-08 | GH #11418 | Parameterised query mismatch in catalog/model/catalog/product.php. Critical – exposes DB internals.
BUG-003 | Reflected XSS via login redirect parameter | Login | Critical | P1 | Open | All browsers | 1. Craft URL: /index.php?route=account/login&redirect=%22%3E%3Cscript%3Ealert(1)%3C/script%3E 2. Open URL in browser | Input is sanitised. No script executes. | Injected script executes in the page. Alert dialog shown. Attacker can steal session cookies or redirect to phishing page. | TC-LL-010 | Security Researcher | 2026-05-08 | CVE-2024-21517 / Snyk SNYK-PHP-7266577 | Fixed in OC 4.1.0.0. Upgrade required. Affects all versions < 4.1.0.0.
BUG-004 | Login fails with PHP TypeError – address_id null | Login / My Account | Critical | P1 | Open | demo.opencart.com – accounts without saved address | 1. Register a new account (no address added) 2. Attempt to log in | User is logged in and redirected to My Account dashboard. | PHP TypeError: getAddress() argument #1 must be int, null given (account/login.php line 212). Login blocked. | TC-LL-001 | QA Team | 2026-05-08 | GH #11418 | Null check missing before calling getAddress(). Add isset($data['address_id']) guard.
BUG-005 | Registration form clears all data on submit without saving | User Registration | High | P1 | Open | Chrome, Firefox – desktop | 1. Go to Account > Register 2. Fill all fields correctly 3. Click Continue | Account is created. User redirected to My Account. | Form resets/clears all entered data. Account is NOT created. No error message shown to explain failure. | TC-UR-001 | QA Team | 2026-05-08 | GH #11418 | Likely server-side validation error not surfaced to UI. Check register.php controller response.
BUG-006 | Cart empty on Safari / iOS after Add to Cart | Shopping Cart | High | P1 | Open | Safari on iPhone / macOS | 1. Open site in Safari 2. Add any product to cart 3. Click the cart icon to view cart | Cart shows the added product with correct quantity. | Cart page shows 'Your shopping cart is empty!' despite the success notification appearing. Only affects Safari/iOS users. | TC-SC-001 / TC-CB-003 | QA Team | 2026-05-08 | OC Forum #231872 | Possible SameSite cookie issue in Safari. Check OCSESSID cookie settings.
BUG-007 | Duplicate customer created with same email via Admin | User Registration / Admin | High | P2 | Open | Admin panel – demo.opencart.com/admin | 1. Log into Admin 2. Go to Customers > Add New 3. Add customer with email X 4. Repeat with exact same email X | Error: email already registered. Second customer not created. | Second customer created with identical email. Two accounts share the same email address – breaks login and uniqueness constraint. | TC-UR-002 | QA Team | 2026-05-08 | GH #11418 | Unique constraint not enforced in Admin customer creation. Add DB-level unique index check.
BUG-008 | PHP Warnings exposed in page header after login | Login / Header | High | P2 | Open | demo.opencart.com – after login | 1. Log in with a registered account 2. Observe the top of any page | No PHP warnings visible. Clean page render. | Multiple PHP Warnings printed at top of page: 'Undefined array key customer_token in header.php lines 67–70'. Leaks internal file paths. | TC-LL-001 | QA Team | 2026-05-08 | GH #11418 | Set error_reporting=0 in production. Fix undefined key in header.php. Exposes server path – security risk.
BUG-009 | Session fixation – OCSESSID allows session hijacking | Authentication / Security | High | P1 | Open | All browsers | 1. Set OCSESSID cookie to a known value 2. Get victim to authenticate 3. Use known OCSESSID + user_token from URL to log in as victim | Session ID regenerated on login. Old OCSESSID invalidated. | Attacker can fix the session ID before auth and hijack the authenticated session without needing credentials. | TC-LL-001 | Security Researcher | 2026-05-08 | GH #12939 | Regenerate session ID on login. Use session_regenerate_id(true).
BUG-010 | Product option not selectable – Canon EOS 5D | Product Page | High | P2 | Open | demo.opencart.com – Canon EOS 5D product | 1. Navigate to the Canon EOS 5D product page 2. Try to select a product option (e.g. colour/size) | Option dropdown is enabled and selectable. | Option selector is unresponsive / disabled. Cannot select any option. Add to Cart proceeds without required option. | TC-PP-011 | QA Team | 2026-05-08 | GH #11418 | Check option data binding in product page JS. Possibly a missing product_option_id in demo data.
BUG-011 | Mini-cart hover text invisible – black text on black background | Shopping Cart / UI | Medium | P3 | Open | All browsers – desktop | 1. Add a product to cart 2. Hover over the mini-cart dropdown items | Text remains readable on hover. Contrasting hover background applied. | On hover, mini-cart item text becomes black against a black background – completely unreadable. Accessibility failure. | TC-SC-010 | QA Team | 2026-05-08 | GH #11418 | CSS: .dropdown-menu li:hover color is inheriting incorrectly. Override with explicit color: #fff or similar.
BUG-012 | Add to Cart button text turns black on hover | Product Page / UI | Medium | P3 | Open | All browsers | 1. Go to any product page 2. Hover over the 'Add to Cart' button | Button text stays white (or high-contrast) on hover. | Button text changes to black on hover making it difficult to read against the button background. | TC-PP-004 | QA Team | 2026-05-08 | GH #11418 | CSS btn-primary:hover color rule missing. Add explicit color: #fff to hover state.
BUG-013 | Newsletter subscribe accepts invalid email formats | Home Page / Newsletter | Medium | P3 | Open | All browsers | 1. Scroll to footer newsletter form 2. Enter 'notanemail' (no @ symbol) 3. Click Subscribe | Validation error: 'Please enter a valid email address'. | Form submits with invalid email. Either success message shown for invalid input, or silent failure with no feedback. | TC-HP-009 / TC-HP-010 | QA Team | 2026-05-08 | - | Add HTML5 type=email validation + server-side regex check.
BUG-014 | Human verification (CAPTCHA) blocks all users on demo | All Pages | Medium | P2 | Open | All browsers / networks | 1. Navigate to demo.opencart.com 2. Attempt to pass CAPTCHA challenge | CAPTCHA passes. User accesses the site normally. | CAPTCHA challenge cannot be completed regardless of browser or network. Site completely inaccessible to legitimate users. | - | QA Team | 2026-05-08 | GH #14678 | CAPTCHA misconfigured on demo server. Review reCAPTCHA site key / domain whitelisting.
BUG-015 | Admin demo login not working intermittently | Admin Panel | Medium | P2 | Open | demo.opencart.com/admin | 1. Go to demo.opencart.com/admin 2. Enter credentials demo/demo 3. Click Login | Admin dashboard loads successfully. | Login fails or returns error. Issue persists across multiple devices and browsers for extended periods (reported as lasting 1+ week). | - | QA Team | 2026-05-08 | GH #14137 | Demo environment instability. May require server-side session/DB reset.
BUG-016 | Return form does not trigger confirmation email | My Account / Returns | Medium | P3 | Open | All environments | 1. Log in 2. Go to My Account > Returns 3. Submit a return request | Confirmation email sent to customer and admin. | No email triggered after return form submission. Customer has no confirmation that return was received. | TC-MA-005 | QA Team | 2026-05-08 | OC Forum – msklut 2020 | Check SMTP config and mail() call in return controller. Possibly missing event hook.
BUG-017 | Currency auto-update fails in v3.0.4.1 | Currency / Settings | Low | P4 | Open | OpenCart 3.0.4.1 | 1. Enable automatic currency update in Admin > System > Settings 2. Wait for scheduled update or trigger manually | Currencies update to current exchange rates. | Currency rates do not update automatically. Manual update also fails silently. | TC-HP-005 | QA Team | 2026-05-08 | OC Forum – johans May 2025 | Bug introduced in 3.0.4.1. Revert to 3.0.4.0 or patch cURL currency fetch.
BUG-018 | Special/discount calendar popup not opening in Admin | Admin / Pricing | Low | P4 | Open | OpenCart 3.0.4.0 Admin | 1. Go to Admin > Catalog > Products > Edit 2. Click on Special Price tab 3. Click date picker for start/end date | Date picker calendar popup opens. | Calendar popup does not open. Date field remains non-interactive. | - | QA Team | 2026-05-08 | OC Forum – lz1nud Dec 2024 | JS conflict with datepicker library. Check bootstrap-datepicker initialisation.
BUG-019 | Page title shows 'Your Store' instead of store name | SEO / Meta | Low | P4 | Open | All browsers | 1. Load any page on demo.opencart.com 2. Check browser tab title | Browser tab shows configured store name. | Browser tab displays default placeholder 'Your Store' instead of a real store name. Poor SEO and branding. | TC-HP-014 | QA Team | 2026-05-08 | - | Update Admin > System > Settings > Store Name. Demo not configured.
BUG-020 | Registration allows names with invalid special characters | User Registration | Low | P4 | Open | All browsers | 1. Register with First Name = '74t7w9z$C #@!' 2. Submit form | Validation error: name should contain letters and spaces only. | Account created successfully with special characters in name field. No input sanitisation on name fields. | TC-UR-009 | QA Team | 2026-05-08 | GH #11418 | Add regex validation: /^[a-zA-Z\s]+$/ on first/last name fields.

## Legend & Metrics
Legend & Bug Metrics
Severity | Description | Bug Metrics Summary
Critical | System crash / data loss / security breach. Release blocker. | Total Bugs | 20
High | Major feature broken. Significantly impacts users. Fix before release. | Critical | 4
Medium | Feature partially broken. Workaround exists. Fix in next sprint. | High | 6
Low | Minor UI/UX issue. Cosmetic. Fix when capacity allows. | Medium | 6
|  | Low | 4
Status | Meaning | Open | 20
New | Just reported, not yet reviewed. | Fixed | 0
Open | Confirmed bug, being worked on. | Security Bugs | 3
Fixed | Fix implemented, pending verification.
Won't Fix | Acknowledged but out of scope / by design.
Duplicate | Already reported in another ticket.